## BOM
DIY Nano Drone — Bill of Materials
Legend: blue text / yellow fill = edit these cells. Status dropdown: Have · To order · Ordered · Received · Verified · Deferred. Est. costs are as of 2026-10-30; verify at checkout.
ID | Order | Category | Item | Spec to verify before buying / on arrival | Qty needed | Qty to buy | Vendor | Link | Est. cost ($) | Actual cost ($) | Status | Notes
01 | A | Flight controller | ESP32-C3 SuperMini (3-pack) | Title says 'SuperMini'; USB-C; BOOT + RESET buttons | 2 | 1 pack | AliExpress (TENSTAR, HongWeiWei) |  | 11.39 | 0 | Received | 1 drone FC, 1 ground station
02 | A | Sensors | GY-521 MPU-6050 (2–3 pack) | On arrival: WHO_AM_I reads 0x68 | 1 | 1 pack | AliExpress (VoltSteed Pro Store) |  | 7 | 6.45 | Received | Spare in case of a bad clone
03 | A | Propulsion | 8520 coreless brushed motor set, 2 CW + 2 CCW | 1.0 mm shaft; 8.5 x 20 mm; ~5 g each | 4 | 1 set | SpeedyFPV | link | 4.49 | 4.49 | Ordered | On sale $4.49 (list $8.99)
04 | A | Propulsion | LDARC 65 mm props, 1 mm shaft (20 pcs) | Listing title says 1 mm shaft; 10 CW + 10 CCW | 4 | 1 pack | AliExpress (Hippogriff Workshop Store) | link | 6.99 | 2.89 | Ordered | Spares for crashes
05 | A | Shipping | SpeedyFPV shipping |  |  |  | SpeedyFPV |  | 1.99 | 1.99 | Ordered | Listed estimate
06 | A | Test rig | 1 kg straight-bar load cell + HX711 | 1 kg capacity (not 5 kg); HX711 80 Hz mode | 1 | 1 kit (4-set ok) | AliExpress (Estardyn Choice Store) | link | 11.19 | 2.19 | Ordered | Thrust stand + precision scale
07 | A | Motor driver | AO3400A N-ch MOSFET, SOT-23 | Datasheet R_DS(on) spec'd at 2.5 V gate | 4 | 10 | AliExpress (IRUWB) | link | 2.82 | 1.59 | Ordered | 100 pcs
08 | A | Motor driver | SS34 Schottky diode, 40 V 3 A | SMA/SMB package; check cathode band | 4 | 10 | AliExpress (Shop1104159084) |  | 2 | 1.79 | Ordered | 90 pcs
09 | A | Motor driver | SOT-23 to DIP adapter boards | Fits SOT-23-3 | 4 | 10 | AliExpress (Ediy) |  | 3 | 2.16 | Ordered | 5 pcs
10 | A | Power | 470 µF electrolytic capacitor | ≥ 10 V rating; low-ESR preferred | 1 | 2 | AliExpress |  | 1 | 3.19 | Ordered | 120 pcs assorted
11 | A | Power | 10 nF ceramic capacitor (103) |  | 1 | 10 | AliExpress (TENSTAR) |  | 1 | 4.19 | Ordered | 300 pcs assorted
12 | A | Remote | SPDT toggle switch |  | 1 | 2 | AliExpress (Ace Wong) |  | 2 | 1.39 | Ordered | 20 pcs
13 | A | Shipping | Order 3 shipping (if any) | [5 empty] | 0 | 0 | Ordered | Fill in at checkout
14 | B | Power | 1S LiPo/LiHV, ~450 mAh, BT2.0 (4-pack) | Chemistry matches charger (4.20 vs 4.35 V) | 2 | 1 pack | BETAFPV / SpeedyFPV |  | 16 |  | Deferred | Est. — verify after Milestone 3
15 | B | Power | 1S charger, BT2.0, matching chemistry | Charge voltage matches battery | 1 | 1 | BETAFPV |  | 8 |  | Deferred | Est. — verify
16 | B | Power | BT2.0 pigtail |  | 1 | 2 | BETAFPV / SpeedyFPV |  | 3 |  | Deferred | Est. — verify
17 | B | Power | 3.3 V buck-boost regulator (Pololu S7V8F3 or equiv.) | Input 2.7 V+; ≥ 500 mA out | 1 | 1 | Pololu |  | 11 |  | Deferred | Est. — verify
18 | B | Mechanical | M2 screws / nylon standoffs kit |  | 1 | 1 kit | Amazon |  | 6 |  | Deferred | Est.
19 | B | Mechanical | Hook-and-loop battery strap |  | 1 | 2 | Amazon |  | 2 |  | Deferred | Est.
20 | Have | Prototyping | Breadboard + M-M / M-F jumpers |  | 1 | 0 | ELEGOO kit |  | 0 |  | Have
21 | Have | Passives | 100 Ω resistors |  | 4 | 0 | ELEGOO kit |  | 0 |  | Have | Gate resistors
22 | Have | Passives | 100 kΩ resistors |  | 6 | 0 | ELEGOO kit |  | 0 |  | Have | Gate pull-downs + battery divider
23 | Have | Passives | 100 nF ceramic (104) |  | 6 | 0 | ELEGOO kit |  | 0 |  | Have | Decoupling
24 | Have | Passives | 10 µF capacitors | ≥ 6.3 V | 2 | 0 | ELEGOO kit |  | 0 |  | Have
25 | Have | Remote | LEDs + momentary button |  | 1 | 0 | ELEGOO kit |  | 0 |  | Have | Status LEDs, kill switch
26 | Have | Materials | PETG filament (1 kg) |  | ~100 g | 0 | On hand |  | 0 |  | Have | Frame, rigs, coupon
27 | Have | Materials | TPU filament |  | ~20 g | 0 | On hand |  | 0 |  | Have | Prop guards
28 | Have | Tools | Bench supply 0–30 V / 0–10 A, multimeter, FNIRSI scope, iron, calipers, data cable, glasses, LiPo bag |  |  | 0 | On hand |  | 0 |  | Have | Verified 2026-10-30
29 | Have | Wiring | Silicone wire 22 AWG + 26–28 AWG, heat-shrink | Confirm you have it |  | 0 | On hand? |  | 0 |  | Have | Change to 'To order' if missing
30 | Later | Remote | KY-023 joystick modules (pair) |  | 2 | 1 pair | Amazon / AliExpress |  | 4 |  | Deferred | Milestone 9 handheld remote
[8 empty] | Totals | 104.87 | 32.32

## Mass Budget
Mass Budget — Milestone 0
Fill yellow cells with vendor-listed masses now (cite the source); replace with load-cell measurements later. Totals and thrust checks compute automatically.
Component | Qty | Est. mass each (g) | Source of estimate | Est. total (g) | Measured each (g) | Measured total (g) | Notes
8520 motor | 4 | 5 | SpeedyFPV listing | 20
65 mm prop | 4 | 0.4 | LDARC listing (SpeedyFPV) | 1.6
1S ~450 mAh battery | 1
ESP32-C3 SuperMini | 1
GY-521 IMU | 1
3.3 V buck-boost regulator | 1
Motor-driver board (MOSFETs, diodes, caps, perfboard) | 1
Wiring + BT2.0 pigtail | 1
Frame (target 10–15 g) | 1
Prop guards | 4
Fasteners, tape, strap, foam | 1
|  |  |  | Estimate |  | Measured
Subtotal (g) |  |  |  | 21.6 |  | 0
Margin for forgotten items |  |  |  | 15%
All-up weight, AUW (g) |  |  |  | 24.84 |  | 0
Hover thrust per motor = AUW/4 (g) |  |  |  | 6.21 |  | 0
Required max thrust per motor for T/W = 2 (g) |  |  |  | 12.42 |  | 0
Max thrust per motor (g) |  |  |  | 27 |  |  | Placeholder: one buyer's review of the SpeedyFPV set reported 27 g. Replace with your thrust-stand result (Milestone 3).
Thrust-to-weight ratio |  |  |  | 4.3478 |  |  | Target ≥ 2.0 for adequate control authority

## Budget
Budget Summary
Project budget ($) | 100
Order A — estimated | 54.87
Order B — estimated | 46
Later (stretch) — estimated | 4
Total estimated (A + B) | 100.87
Remaining after estimate (A + B) | -0.87
Actual spent to date | 32.32
Remaining vs. actual | 67.68
Status counts
Have | 10
To order | 0
Ordered | 11
Received | 2
Verified | 0
Deferred | 7